## Estimation Template
Releaseplanung Project Temperature/Pressure System
| Sample-Phase | A-Sample | [13 empty] | B-Sample | [13 empty] | C-Sample | [13 empty] | SOP | [13 empty] | Parameter
| Release: | A010 | [6 empty] | A020 | [6 empty] | B010 | [6 empty] | B020 | [6 empty] | C010 | [6 empty] | C020 | [6 empty] | 0001 | [6 empty] | 0002 | [7 empty] | Probability | 80%
| Planned Releasedate | 2013-03-19 | [6 empty] | 2013-07-12 | [6 empty] | 2013-10-21 | [6 empty] | 2013-12-18 | [6 empty] | 2014-03-18 | [6 empty] | 2014-05-22 | [6 empty] | 2014-09-22 | [6 empty] | 2014-11-22 | [7 empty] | €/hours | 65
Feature by Phase | Mechanics - housing features | 0% | [6 empty] | 30%
| Mechanics - addon features | - | [6 empty] | - | [49 empty] | meaning | Unit
| Electronics - basic features | 0% | [6 empty] | 40% | [48 empty] | X = | will be used | -
| Electronics - addon features | - | [6 empty] | - | [48 empty] | N = | Nano-percent value | hours (work)
| Software - basic features | 0% | [6 empty] | 20% | [48 empty] | E = | Expected value | hours (work)
| Software - addon features | - | [6 empty] | - | [48 empty] | U = | Uncertainty factor | 1 .. 10
| Optics - basic features | - | [6 empty] | - | [48 empty] | W = | Worst-case value | hours (work)
| Optics - addon features | - | [6 empty] | -
| Actors - basic features | - | [6 empty] | -
| Actors - addon features | - | [6 empty] | -
| Sensors - basic features | 0% | [6 empty] | 50%
| Sensors - addon features | - | [6 empty] | -
| Diagnostics | 0% | [6 empty] | 30%
| Diagnostic Tools | - | [6 empty] | -
Systems requirements |  | X | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work
| Collect customer requirements | x | 45 | 70 | 6 | 270 | 80% | 175.1317 | x | 35 | 70 | 5 | 175 | 80% | 120.7782
| Evaluate customer requirements | x | 35 | 70 | 5 | 175 | 80% | 120.7782 | x | 35 | 70 | 5 | 175 | 80% | 120.7782
| Create systems requirements specification | x | 60 | 90 | 3 | 180 | 80% | 133.5242
| Update systems requirements specification | [7 empty] | x | 35 | 70 | 3 | 105 | 80% | 82.8641
| Total hours | [5 empty] | 80% | 429.4341 | [5 empty] | 80% | 324.4205 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
Systems architecture |  | X | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work
| Define systems boundary | x | 20 | 45 | 4 | 80 | 80% | 59.5061
| Develop chain of constrains | x | 50 | 70 | 5 | 250 | 80% | 165.1472
| Allocate systems requirements | x | 30 | 67 | 4 | 120 | 80% | 89.1131
| Create systems architecture specification | x | 70 | 120 | 6 | 420 | 80% | 275.0862
| Update systems architecture specification | [7 empty] | x | 20 | 36 | 4 | 80 | 80% | 57.0217
| Total hours | [5 empty] | 80% | 588.8526 | [5 empty] | 80% | 57.0217 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
Detailed requirements |  |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work
| Evaluate systems requirements | x | 20 | 45 | 4 | 80 | 80% | 59.5061 | x | 5 | 15 | 3 | 15 | 80% | 13.9443
| Create mechanic requirements specification | x | 15 | 25 | 4 | 60 | 80% | 42.2518
| Create electronic requirements specification | x | 30 | 67 | 4 | 120 | 80% | 89.1131
Create optical requirements specification
| Create software requirements specification | x | 10 | 23 | 3 | 30 | 80% | 24.7085
| Update mechanic requirements specification | [7 empty] | x | 10 | 23 | 5 | 50 | 80% | 35.3031
| Update electronic requirements specification | [7 empty] | x | 35 | 70 | 5 | 175 | 80% | 120.7782
Update optical requirements specification
| Update software requirements specification | [7 empty] | x | 15 | 25 | 4 | 60 | 80% | 42.2518
| Total hours | [5 empty] | 80% | 215.5795 | [5 empty] | 80% | 212.2773 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
Detailed design |  |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work
| Create mechanic component design | x | 30 | 38 | 7 | 210 | 80% | 131.3107
| Create electronic component design | x | 23 | 56 | 4 | 92 | 80% | 69.711
Create optical component design
| Create software high level design | x | 30 | 67 | 4 | 120 | 80% | 89.1131
| Create software low level design | x | 10 | 23 | 3 | 30 | 80% | 24.7085
| Update mechanic component design | [7 empty] | x | 10 | 23 | 5 | 50 | 80% | 35.3031
| Update electronic component design | [7 empty] | x | 35 | 70 | 5 | 175 | 80% | 120.7782
Update optical component design
| Update software high level design | [7 empty] | x | 15 | 25 | 4 | 60 | 80% | 42.2518
| Update software low level design | [7 empty] | x | 5 | 15 | 3 | 15 | 80% | 13.9443
| Total hours | [5 empty] | 80% | 314.8433 | [5 empty] | 80% | 212.2773 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
Component development |  |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work
Develop mechanic components
Develop electronic components
Develop optical components
Develop software modules
Update mechanic components
Update electronic components
Update optical components
Update software components
| Total hours | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
Divison tests |  |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work
Mechanical system test
Electronical system test
Optical system test
Software system test
| Total hours | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
System tests |  |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work
| Setup test concept (Sys+HW+SW) | x | 8 | 16 | 4 | 32 | 80% | 23.2364
| Setup system test concept | x | 10 | 16 | 2 | 20 | 80% | 17.1716
EMC tests
Climate tests
Environments tests
Customer tests
Systemtest
Develop test plan
Documentation
| Total hours | [5 empty] | 80% | 40.408 | [5 empty] | 0 | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
Production |  |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work
Logistics and resource planning
Measurement planing
Develop production concept
Setup manufacturing equipments
| Total hours | [6 empty] | 0 | [5 empty] | 0 | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
Management |  |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work
| Meetings | x | 30 | 80 | 3 | 90 | 80% | 78.9898
| Project management | x | 80 | 160 | 4 | 320 | 80% | 232.3644
| Risk management | x | 20 | 45 | 5 | 100 | 80% | 70.3352
| Total hours | [5 empty] | 80% | 381.6894 | [5 empty] | 0 | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
Support |  |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work |  | N | E | U | W | % | work
| Quality management | x | 16 | 24 | 6 | 96 | 80% | 62.0589
| Configuration management | x | 24 | 48 | 5 | 120 | 80% | 82.8194
Release management
| Total hours | [5 empty] | 80% | 144.8782 | [5 empty] | 0 | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
Overall | [7 empty] | work | [6 empty] | work | [6 empty] | work | [6 empty] | work | [6 empty] | work | [6 empty] | work | [6 empty] | work | [6 empty] | work
| Engineering | [6 empty] | 1548.7095 | [6 empty] | 805.9969 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| Testing | [6 empty] | 40.408 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| Production | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| Management | [6 empty] | 381.6894 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| Support | [6 empty] | 144.8782 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| Total hours | [6 empty] | 2115.6852 | [6 empty] | 805.9969 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
| Total budget | 137519.5359 | [6 empty] | 52389.8002 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0